## Sheet1
ID | Risk description | Likelihood | Impact if the risk occurs | Severity | Owner | Mitigating action | Category
1 | Releasing the software with a bug on Day 1 | High | Low | Low | Developer | Debug and test the software thoroughly to try and catch as many potential bugs as possible. | Technology
2 | Security risks with software, specifically on the database side | Low | High | Medium | Developer | Consistently update Security Policies and revamp the current security in place. Additionally, keeping up with security practices as they evolve. | Technology
3 | Competitors realase similar product before our company | Low | High | High | Project manager | Contact supplyers, set up pro-active exclusivity deals | Market
4 | Product secrets are leaked to media devaluing product. | Medium | Medium | Medium | Developer | Set strict seuciry mesures, when share devleopment information | Market
5 | Key members of our development team have left the project, leaving not enough developers to keep the current baseline timeframe | Low | High | High | Project Manager | Constantly look for talent in the job market while also keeping current team members satisifed and happy with their current role. | People
6 | One of our current developers is secretly selling source code and information about the project to competitors | Low | High | High | Project Manager | require staff sign NDAs, limit soruce code access base on role | People
7 | Employee currently working from home and at brick and mortar location depend on internet to communicate with each other, any outage will disrupt team communication | Medium | High | High | Technical communications | Work with ISP's to keep network connection up and stable for employees. Also have backup connections for employees incase of main netwrok going down. | Structure/process
8 | Our current brick and mortar location still requires employees to be attending to it for the project even with the current covid 19 pandemic | High | Medium | Medium | Management | Have management implement a strict health policy for all employees to follow so that all employees in the location will be safe. Also have equipment to keep employees safe | Structure/process
9 | Current spending patterns in project are to high to yield financial benefit from the project | Medium | Medium | Medium | Project Manager | Retool the current spending patterns and see were costs can be cut to make the project financially viable | Financial
10 | Current spending over the baseline amount set for the overall project | Medium | Low | Low | Project Manager | Review tasks to see were over spending can be cut | Financial